## Read me
The sapperment transformation-structure self-check
Twenty-four statements across six dimensions of SAP transformation structure. Score each honestly; the verdict tells you whether your programme is steerable.
How to score
For each statement on "Self-check", enter 0, 1 or 2 in the blue Score column:
0 = not true for us · 1 = partly true / informal · 2 = true, documented and owned
The "Result" sheet computes your total (max 48), per-dimension scores and the verdict band.
The bands
0-16 UNSTRUCTURED — decisions and architecture are implicit; start with ownership, not tooling.
17-32 EMERGING — structure exists in patches; close the gaps before scaling the programme.
33-48 STEERABLE — the programme can absorb change; keep measuring value after go-live.
One EXAMPLE row shows the expected format — replace its score with your own.
An independent sapperment worksheet — www.sapperment.com/sap-executive-clarity/transformation-governance/ — not affiliated with SAP SE.

## Self-check
Dimension | Statement | Score (0-2)
EXAMPLE | EXAMPLE — The programme has a single accountable executive sponsor. | 2
Decision structure | Every major transformation decision has a named owner and a written record of the trade-offs.
The deployment model (public/private/two-tier) was decided against criteria, not inherited.
We can state which decisions the board owns and which the programme owns.
Decisions unmade are visible as risks, not hidden as assumptions.
Architecture principles | A clean-core / fit-to-standard policy exists and is enforced in change decisions.
There is a documented rule for where custom logic lives (core vs. platform extensions).
Deviations from standard require a business case, not a preference.
The instance strategy (one core or several) is an explicit, recorded decision.
Landscape clarity | We have a current map of systems, integrations and data flows the programme touches.
Data-residency and regulatory constraints on the landscape are documented.
Legacy decommissioning is planned with dates and owners, not "later".
Carve-in/carve-out (M&A) requirements are part of the architecture, not an afterthought.
Economics | A multi-year baseline exists: what the current landscape really costs, including internal effort.
Every claimed benefit has a named business owner who will report it after go-live.
We know which assumptions would change the decision if they moved 20%.
Running costs of the target model are priced beyond year one.
Operating model | The run organisation (roles, release rhythm, support) is designed before go-live.
Adoption is owned by the business, with training and process ownership resourced.
Release upgrades are treated as routine operations, not projects.
Innovation outside the core (platform, AI, analytics) has a defined path to production.
Governance & evidence | Steering meetings review a shared fact base, with facts separated from opinion.
Programme status reports outcomes and risks, not activity.
Value realisation is reviewed after go-live on a fixed rhythm.
Escalation paths are defined and were agreed before they were needed.

## Result
Your result
Dimension | Score | of max
Decision structure |  | 8
Architecture principles |  | 8
Landscape clarity |  | 8
Economics |  | 8
Operating model |  | 8
Governance & evidence |  | 8
TOTAL |  | 48
Verdict
Next step: bring the two weakest dimensions to the steering committee — as decisions with owners, not observations.
An independent sapperment worksheet — www.sapperment.com — not affiliated with SAP SE.